| Hermits Peak/Calf Canyon BAER Implementation Interim Report December 2022 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2500-8/Forest | Line Items | Units | Unit Cost | # of Units | BAER $ Requested | BAER $ Authorized | Completed | BAER $ Expended | BAER $ Remaining | Notes |
| Initial/SFNF | Protection/Safety |  |  |  |  |  |  |  |  |  |
|  | Road/Trail Hazard/Closure Signs | job | $34,925 | 1 | $34,925 | $34,925 | 9/10/2022 | $34,925 | $0 |  |
|  | Toilet/Septic Pumping | per | $1,500 | 9 | $13,500 | $13,500 | 7/15/2022 | $10,700 | $2,800 |  |
|  | Infrastructure Removal | job |  | 1 | $25,500 | $25,500 | 7/15/2022 | $15,000 | $10,500 |  |
| Initial/SFNF Total |  |  |  |  | $73,925 | $73,925 |  | $60,625 | $13,300 |  |
| Interim 1/SFNF | Land Treatments |  |  |  |  |  |  |  |  |  |
|  | Aerial Mulching | acres | $1,400 | 3387 | $4,741,800 | $5,992,000 | 9/4/2022 | $3,566,150 | $2,425,850 |  |
|  | Aerial Seeding | acres | $160 | 9428 | $1,508,480 | $0 | 8/30/2022 | $0 | $0 | BAR Funds |
|  | Cultural/Heritage Resource Protection |  | $13,880 | 1 | $13,880 | $13,880 | 6/29/2022 | $5,000 | $8,880 |  |
|  | RMRS Level 3 Monitoring | per | $50,000 | 1 | $0 | $50,000 | Ongoing |  | $50,000 |  |
| Interim 1/SFNF | Roads and Trails |  |  |  |  |  |  |  |  |  |
|  | Storm Proofing | miles | $2,868 | 12.8 | $36,710 | $36,710 | 6/22/2022 | $36,000 | $710 |  |
|  | Storm I&R | miles | $19,018 | 12.8 | $243,430 | $243,430 | Ongoing | $87,900 | $155,530 | $100,000 committed to SI&R BPA |
|  | Emergency Crossing | job | $10,963 | 1 | $10,963 | $10,963 | 10/29/2022 | $0 | $10,963 | FA |
|  | Culvert/Dips | culverts | $692 | 30 | $20,760 | $20,760 | 6/22/2022 | $20,000 | $760 |  |
|  | Channel Clearing | sites | $2,309 | 15 | $34,635 | $34,635 | 6/22/2022 | $34,000 | $635 |  |
| Interim 1/SFNF | Protection/Safety |  |  |  |  |  |  |  |  |  |
|  | Waste Removal | job | $7,631 | 3 | $22,893 | $22,893 | 6/29/2022 | $8,000 | $14,893 |  |
|  | Coir fiber wattles | per | $150 | 100 | $15,000 | $15,000 | 7/15/2022 | $12,000 | $3,000 |  |
| Interim 1/SFNF Total |  |  |  |  | $6,648,551 | $6,440,271 |  | $3,769,050 | $2,671,221 |  |
| Interim 2/SFNF | Land Treatments |  |  |  |  |  |  |  |  |  |
|  | Cultural/Heritage Resource Protection | site | $524 | 13 | $6,812 | $7,000 | 8/16/2022 | $0 | $7,000 | Hazard tree felling - FA |
| Interim 2/SFNF | Road and Trails |  |  |  |  |  |  |  | $0 |  |
|  | Storm Proofing | miles | $6,000 | 3.25 | $19,500 | $19,500 | 7/9/2022 | $15,500 | $4,000 |  |
|  | Storm I&R | miles | $20,000 | 3.25 | $65,000 | $65,000 | Ongoing | $30,000 | $35,000 |  |
|  | New Dip | each | $7,500 | 2 | $15,000 | $15,000 | 7/9/2022 | $12,000 | $3,000 |  |
|  | Improve Dip | each | $2,000 | 14 | $28,000 | $28,000 | 7/9/2022 | $20,500 | $7,500 |  |
|  | Fill Slope Armoring | site | $1,000 | 2 | $2,000 | $2,000 | 7/9/2022 | $2,000 | $0 |  |
|  | Contract Admin | job | $24,110 | 1 | $24,110 | $20,960 | Completed | $20,960 | $0 |  |
| Interim 2/SFNF | Protection/Safety |  |  |  |  |  |  |  | $0 |  |
|  | FW8-18C, 36X36 | sign | $725 | 12 | $8,700 | $8,700 | 9/10/2022 | $8,700 | $0 |  |
|  | TFW8-14f, 26X12 | sign | $530 | 10 | $5,300 | $5,300 | 9/10/2022 | $5,300 | $0 |  |
|  | Guardrail Repair | job | $9,825 | 1 | $9,825 | $20,000 | On hold | $0 | $20,000 |  |
| Interim 2/SFNF Total |  |  |  |  | $184,247 | $191,460 |  | $114,960 | $76,500 |  |
| Interim 2/CNF | Road and Trails |  |  |  |  |  |  |  |  |  |
|  | Storm Proofing | miles | $6,000 | 5 | $32,160 | $32,160 |  | $0 | $32,160 |  |
|  | SI&R | miles | $19,700 | 6 | $116,427 | $116,427 | Ongoing | $0 | $116,427 | BPA |
|  | SI&R | event | $17,600 | 3 | $52,800 | $52,800 | Ongoing | $0 | $52,800 |  |
|  | Dip Construction | each | $7,500 | 4 | $30,000 | $30,000 |  | $0 | $30,000 |  |
|  | Remove Bridge | job | $15,000 | 1 | $15,000 | $15,000 | 6/28/2022 | $13,010 | $1,990 |  |
|  | Contract Admin | job | $23,550 | 1 | $23,550 | $20,400 | Completed | $20,400 | $0 |  |
| Interim 2/CNF | Protection/Safety |  |  |  |  |  |  |  |  |  |
|  | P1-FW8-18C, 36 X 36 | sign | $725 | 15 | $10,875 | $10,875 | - | - | - |  |
|  | P1-TFW8-14d, 12 X 10 | sign | $450 | 20 | $9,000 | $9,000 | - | - | - |  |
|  | P1-TFW8-14d, 24 X 16 | sign | $530 | 12 | $6,360 | $6,360 | - | - | - |  |
|  | P1-TFW8-14f, 26 X 12 | sign | $530 | 40 | $21,200 | $21,200 | - | - | - |  |
|  | Hazard Warning Signs (Combined) | - | - | - | - | $47,435 | Ongoing | $22,200 | $25,235 | Total for all CNF signs |
|  | P2-Road Closure Barrier | each | $350 | 24 | $8,400 | $8,400 | Completed | $3,200 | $5,200 |  |
| Interim 2/CNF Total |  |  |  |  | $325,772 | $322,622 |  | $58,810 | $263,812 |  |
| Interim 3/SFNF | Road and Trails |  |  |  |  |  |  |  |  |  |
|  | NFSR Bridge SI&R | event | $3,000 | 8 | $24,000 | $0 | NA | NA | NA |  |
|  | Storm Proofing | miles | $6,000 | 6 | $33,000 | $33,000 | 8/31/2022 | $33,000 | $0 |  |
|  | SI&R | event | $4,000 | 22 | $88,000 | $88,000 | Ongoing | $15,000 | $73,000 |  |
|  | Crossing Proofing | crossing | $2,000 | 2 | $4,000 | $4,000 | 8/31/2022 | $4,000 | $0 |  |
|  | Gates | gate | $20,000 | 5 | $100,000 | $100,000 | Ongoing | $0 | $100,000 | $47,200 committed |
| Interim 3/SFNF | Protection/Safety |  |  |  |  |  |  |  |  |  |
|  | FW8-14d 48X30 | sign | 350 | 2 | $700 | $700 | 9/10/2022 | $700 | $0 |  |
|  | FW8-18a 24X24 | sign | 250 | 9 | $2,250 | $2,250 | 9/10/2022 | $2,250 | $0 |  |
|  | TFW8-14d 12X10 | sign | 150 | 3 | $450 | $450 | 9/10/2022 | $450 | $0 |  |
|  | Vaulted Toilet Pumping | each | 1,500 | 2 | $3,000 | $3,000 | On Hold | $0 | $3,000 |  |
| Interim 3/SFNF Total |  |  |  |  | $255,400 | $231,400 |  | $55,400 | $176,000 |  |
| Totals |  |  |  |  | $7,487,895 | $7,259,678 |  | $4,058,845 | $3,200,833 |  |