## RequestSummary
Burned Area Rehabilitation Funding Request
Region: | 6
Forest: | WWNF
Fire(s): | Double Creek, Nebo, Sturgill
Contact: | Jeff Evans, Mary Young
Date: | 2023-02-21
Pinyon folder link: | https://usfs.box.com/s/88zbstjmn0tqtsmyfse9f6z841b2s4os
Total request: | 1823283.46
For more information see the Burned Area Rehabilitation SP Site.
Category | Project Type | Activity Name (Each activity needs an "ProjectActivityInformation" tab.) | Fire Name | Unit | Units Needed | Cost/Unit | Funds Requested | Priority | Notes and additional information for review.
Category 1 - Minor Facilities and Infrastructure | Non-Range Fences | Reconstruction of Memaloose Horse Pasture Fence | Double Creek | miles | 2.65 | 37399 | 99109 | Moderate | includes material and reconstruction cost
Category 1 - Minor Facilities and Infrastructure | Non-Range Fences | Granny View Overlook Boundary Fence | Double Creek | miles | 0.2 | 40280 | 8069 | Moderate | includes material and reconstruction cost
Category 1 - Minor Facilities and Infrastructure | Non-Range Fences | Removal and Reconstruction of ecology plot fences | Double Creek | miles | 2.18 | 105275 | 234888.46 | Low | Includes removal of burnded fence, material, and reconstruction of new fence. Would consider a partial funding to just remove the fence and not reconstruct
Category 1 - Minor Facilities and Infrastructure | Range | 50/50 cost share of materail and labor for fence reconstruction | Double Creek | miles | 6 | 38280 | 229680 | High | Material is about 20% of reconstruction cost. Labor is about 80% of reconstruction cost. 50/50 cost share is $210,000. requested funds are for material and labor upto 50% of anticipated cost.
Category 1 - Minor Facilities and Infrastructure | Rec Facilities | Burned Buildings Clean-up High | Double Creek | Ea | 4 | 22500 | 90000 | High | Dorrance and Marks
Category 1 - Minor Facilities and Infrastructure | Rec Facilities | Burned Buildings Clean-up Low | Double Creek | Ea | 2 | 17500 | 35000 | Low | Schaeffer and Granny View
Category 1 - Minor Facilities and Infrastructure | Rec Facilities | Double Creek Rec Site Repairs | Double Creek | See Activity Tab | See Activity Tab | See Activity Tab | 117168 | High
Category 1 - Minor Facilities and Infrastructure | Signs | Double Creek Sign Replacement | Double Creek | See Activity Tab | See Activity Tab | See Activity Tab | 46492 | High
Category 1 - Minor Facilities and Infrastructure | Signs | Nebo Sign Replacement | Nebo | See Activity Tab | See Activity Tab | See Activity Tab | 1976 | High
Category 1 - Minor Facilities and Infrastructure | Signs | Sturgill Sign Replacement | Sturgill | See Activity Tab | See Activity Tab | See Activity Tab | 2624 | High
Category 1 - Minor Facilities and Infrastructure | Trails | Double Creek Trail Damage Repair | Double Creek | mile | 108 | 2500 | 270000 | High
Category 1 - Minor Facilities and Infrastructure | Trails | Double Creek Boardwalk Reconstruction | Double Creek | See Activity Tab | See Activity Tab | See Activity Tab | 305625 | High
Category 1 - Minor Facilities and Infrastructure | Trails | Nebo Trail Damage Repair | Nebo | mile | 4 | 4063 | 16252 | High
Category 1 - Minor Facilities and Infrastructure | Trails | Nebo Trail Bridges Reconstruction | Nebo | See Activity Tab | See Activity Tab | See Activity Tab | 142600 | High
Category 1 - Minor Facilities and Infrastructure | Trails | Sturgill Trail Damage Repair | Sturgill | mile | 3 | 6300 | 18900 | High
Category 2 - Lands Unlikely to Recover Naturally | Invasive Plant Treatments | Protection Area Invasive Plant Treatments | Double Creek | Acres | 62 | 400 | 24800 | High | Previously funded by BAER: 10% of survey acres resulting in treatments - (outyear treatments)
Category 2 - Lands Unlikely to Recover Naturally | Invasive Plant Treatments | Suppression Disturbance Invasive Plant Treatments | Double Creek | Acres | 165 | 300 | 49500 | High | Previously funded by BAER: 10% of survey acres (EDRR treatments) from BAER request, buffered at 100ft.
Category 2 - Lands Unlikely to Recover Naturally | Invasive Plant Treatments | Suppression Disturbance Invasive Plant Treatments | Nebo | Acres | 51 | 300 | 15300 | High | New request - not covered in BAER (Outyear treatments requested for 3 seasons)
Category 2 - Lands Unlikely to Recover Naturally | Invasive Plant Treatments | Suppression Disturbance Invasive Plant Treatments | Sturgil | Acres | 171 | 300 | 51300 | High | New request - not covered in BAER (Outyear treatments requested for 3 seasons)
Category 2 - Lands Unlikely to Recover Naturally | Revegetation | Protection Area Preventative Native Seeding | Double Creek | Acres | 86 | 400 | 34400 | High | Includes native seed purchase + application. (7 acres previously funded by BAER in TES site)
Category 2 - Lands Unlikely to Recover Naturally | Revegetation | Suppression Disturbance Preventative Native Seeding | Nebo | Acres | 17 | 400 | 6800 | High | New request - not covered in BAER (Seeding will occur after all treatments completed)
Category 2 - Lands Unlikely to Recover Naturally | Revegetation | Suppression Disturbance Preventative Native Seeding | Sturgil | Acres | 57 | 400 | 22800 | High | New request - not covered in BAER (Seeding will occur after all treatments completed)

## Memaloose Admin Horse Pasture F
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Non-Range Fences
Activity Name: | Allotment and pasture boundary fence reconstruction labor
Describe the fire damage and how the project is addressing that specific damage: | Becuase of the shallow soil, rock outcrops, and availability of wood for constructing fences many fences here are constructed with rock crib corners, rock jack line posts and wood stays to hold the wire spacing. All of this wood material is burned during fires. When the wood burns it weekens the wire adn burns the galvanization off leading to rusty weakened wire that breaks when stretched. We have proposed to replace the corner post, h braces, and gate post with approximately 3 inch metal post that have similar sized metal braces and to replace the wood fence stays with t post as these are nearly permanent structures that do not burn and descrease the maintenance and reconstruction effort once installed.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The category is minor facilities and infrastructure damaged or destroyed by the fire and the project type is structural range improvements. The affected Permittees are in good standing, do not have permit violations, and have previously maintained and reconstructed pasture and allotment boundary fences. The proposed fences for reconstructed were maintained to a satisfactory condition prior to being damaged or destroyed by the fire. The fences proposed for reconstruction are necessary for managing the livestock within the allotments and pastures to meet desired conditions as described in the Forest Plan, NEPA, and consultation for ESA species and within the terns of grazing permits. This proposal is for the Forest Service to procure the material and the Permitee to provide the laber. Becuase of the difference in the cost of material vs labor this is a cost share of about 20% Forest Service and 80% Permittee.
Design/construction specs: | 3 or 4 barbed wire fence with the number of wires indicated by the location and amount of cattle pressure the fence recieves. Wires spaced with the top wire at 38 to 42 inches from the high side, next wire down 10 to 12 inches from the top wire. Bottom wire 16 to 18 inches from the ground and if a 4 th wire then evenly spaced between bottom and 3rd wire from bottom. T post at about 13 foot intervals with the post moved closer if necessary. May be necessary to drill and pilot hole and then drive the t post into rock upto or beyond the spade. Wires are attached to t post using wire or t post clips. 2 7/8 metal posts can be driven with a heavy driver or a pilot hole drilled and the post driven with a heavy driver. These post should be braced in one direction if an end post or in two directions if fence is constructed in two direction. Brace may be welded or mechanically fastened to post about the location of the middle wires and be dug into or concreted into rock for solid support of the post. Fences are constructed in 1/4 mile or less sections with corner post at ends, corners, major elevation changes or inflection points.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
labor for reconstruction | 31680 | 2.65 | 83952
0
studded t post 5.5ft by 1.33lbs ft painted with anchor and fasteners | 7 | 1078 | 7546
12.5 ga double strand galvanized barb wire 1250 feet by 72lbs per roll with barbs about each 4 inches | 124 | 34 | 4216
12.5 gauge double strand twisted Smooth wire | 105 | 11 | 1155
7ft x 2 7/8 hvy wall steel pipe, 7 ft x 2 3/8 hvy wall steel pipe, 1 joint | 110 | 4 | 440
7ft x 2 7/8 hvy wall steel pipe, 2 x 7 ft x 2 3/8 hvy wall steel pipe, 2 joints | 150 | 12 | 1800
Total funding requested: |  |  | 99109

## Granny View Boundary Fence
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Non-Range Fences
Activity Name: | Reconstruction of recreation facility boundary fence
Describe the fire damage and how the project is addressing that specific damage: | Becuase of the shallow soil, rock outcrops, and availability of wood for constructing fences many fences here are constructed with rock crib corners, rock jack line posts and wood stays to hold the wire spacing. All of this wood material is burned during fires. When the wood burns it weekens the wire adn burns the galvanization off leading to rusty weakened wire that breaks when stretched. We have proposed to replace the corner post, h braces, and gate post with approximately 3 inch metal post that have similar sized metal braces and to replace the wood fence stays with t post as these are nearly permanent structures that do not burn and descrease the maintenance and reconstruction effort once installed.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The category is minor facilities and infrastructure damaged or destroyed by the fire and the project type is structural range improvements. The affected Permittees are in good standing, do not have permit violations, and have previously maintained and reconstructed pasture and allotment boundary fences. The proposed fences for reconstructed were maintained to a satisfactory condition prior to being damaged or destroyed by the fire. The fences proposed for reconstruction are necessary for managing the livestock within the allotments and pastures to meet desired conditions as described in the Forest Plan, NEPA, and consultation for ESA species and within the terns of grazing permits. This proposal is for the Forest Service to procure the material and the Permitee to provide the laber. Becuase of the difference in the cost of material vs labor this is a cost share of about 20% Forest Service and 80% Permittee.
Design/construction specs: | 3 or 4 barbed wire fence with the number of wires indicated by the location and amount of cattle pressure the fence recieves. Wires spaced with the top wire at 38 to 42 inches from the high side, next wire down 10 to 12 inches from the top wire. Bottom wire 16 to 18 inches from the ground and if a 4 th wire then evenly spaced between bottom and 3rd wire from bottom. T post at about 13 foot intervals with the post moved closer if necessary. May be necessary to drill and pilot hole and then drive the t post into rock upto or beyond the spade. Wires are attached to t post using wire or t post clips. 2 7/8 metal posts can be driven with a heavy driver or a pilot hole drilled and the post driven with a heavy driver. These post should be braced in one direction if an end post or in two directions if fence is constructed in two direction. Brace may be welded or mechanically fastened to post about the location of the middle wires and be dug into or concreted into rock for solid support of the post. Fences are constructed in 1/4 mile or less sections with corner post at ends, corners, major elevation changes or inflection points.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
labor for reconstruction | 31680 | 0.2 | 6336
0
studded t post 5.5ft by 1.33lbs ft painted with anchor and fasteners | 7 | 81 | 567
12.5 ga double strand galvanized barb wire 1250 feet by 72lbs per roll with barbs about each 4 inches | 124 | 4 | 496
12.5 gauge double strand twisted Smooth wire | 105 | 0 | 0
7ft x 2 7/8 hvy wall steel pipe, 7 ft x 2 3/8 hvy wall steel pipe, 1 joint | 110 | 2 | 220
7ft x 2 7/8 hvy wall steel pipe, 2 x 7 ft x 2 3/8 hvy wall steel pipe, 2 joints | 150 | 3 | 450
Total funding requested: |  |  | 8069

## Ecology Plot Fence
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Non-Range Fences
Activity Name: | Ecology Plot fence remove and reconstrcut
Describe the fire damage and how the project is addressing that specific damage: | The ecology plots are fenced with 8 feet tall fences that have wood posts. These posts have burned and the fence has fallen down. The wire is galvanized. The fire burns the garvanizing off the wire to allow the wire to rust and break during maintenance. We propose to reconstructe the fence with metal posts that are not affected by most fires and replace the wire.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The category is minor facilities and infrastructure. The infrastructure is fencing to exclude all large animals that eat grass, cows that eat grass and a no fence portaion that allows use from all animals. This is non range fence becuase the ecology plots support the wildlife, soil, timber, ecology, and range programs.
Design/construction specs: | The wildlife enclosures are 4 sides each 200 feet long and 8 feet tall. The wire is game/wildlife/field fence that does not allow deer, elk, sheep, goats, and cows to enter. There are double h braces at each corner and an h brace at the gate. Posts are each 8 feet alternatning t post or previously wood 8 inch posts. The wood 8 inch posts can be replaced by oilfield pipe posts that will not be affected by most fires. The enclosure that does not allow cattle is 400 feet on each side with double h braces at the corners and an H brace at the gate. The wire is 4 strand high tensile smooth wire.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
material | 27931 | 2.18 | 60889.58
construction | 39908 | 2.18 | 86999.44
removal of burned fence | 39908 | 2.18 | 86999.44
0
0
0
Total funding requested: |  |  | 234888.46

## Pasture fence 50% costshare
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Range
Activity Name: | 50/50 cost share of matereal and labor for fence reconstruction
Describe the fire damage and how the project is addressing that specific damage: | Becuase of the shallow soil, rock outcrops, and availability of wood for constructing fences many fences here are constructed with rock crib corners, rock jack line posts and wood stays to hold the wire spacing. All of this wood material is burned during fires. When the wood burns it weekens the wire adn burns the galvanization off leading to rusty weakened wire that breaks when stretched. We have proposed to replace the corner post, h braces, and gate post with approximately 3 inch metal post that have similar sized metal braces and to replace the wood fence stays with t post as these are nearly permanent structures that do not burn and descrease the maintenance and reconstruction effort once installed.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The category is minor facilities and infrastructure damaged or destroyed by the fire and the project type is structural range improvements. The affected Permittees are in good standing, do not have permit violations, and have previously maintained and reconstructed pasture and allotment boundary fences. The proposed fences for reconstructed were maintained to a satisfactory condition prior to being damaged or destroyed by the fire. The fences proposed for reconstruction are necessary for managing the livestock within the allotments and pastures to meet desired conditions as described in the Forest Plan, NEPA, and consultation for ESA species and within the terns of grazing permits. This proposal is for the Forest Service to procure the material and the Permitee to provide the laber. Becuase of the difference in the cost of material vs labor this is a cost share of about 20% Forest Service and 80% Permittee. This proposal is for 50% cost share of the Forest Service and the Permitee. The Forest Service would procure the material, install the end posts, corner post, and post with double braces adn then install wires until funds are expended.
Design/construction specs: | 3 or 4 barbed wire fence with the number of wires indicated by the location and amount of cattle pressure the fence recieves. Wires spaced with the top wire at 38 to 42 inches from the high side, next wire down 10 to 12 inches from the top wire. Bottom wire 16 to 18 inches from the ground and if a 4 th wire then evenly spaced between bottom and 3rd wire from bottom. T post at about 13 foot intervals with the post moved closer if necessary. May be necessary to drill and pilot hole and then drive the t post into rock upto or beyond the spade. Wires are attached to t post using wire or t post clips. 2 7/8 metal posts can be driven with a heavy driver or a pilot hole drilled and the post driven with a heavy driver. These post should be braced in one direction if an end post or in two directions if fence is constructed in two direction. Brace may be welded or mechanically fastened to post about the location of the middle wires and be dug into or concreted into rock for solid support of the post. Fences are constructed in 1/4 mile or less sections with corner post at ends, corners, major elevation changes or inflection points.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
reconstruction effor/labor | 38280 | 5.5 | 229680
0
0
0
0
Total funding requested: |  |  | 229680

## Burned Buildings Cleanup High
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Rec Facilities
Activity Name: | Burned Recreation Buildings and Site Cleaup
Describe the fire damage and how the project is addressing that specific damage: | Within the Double Creek Fire area, the Forest had four recreation program support buildings destroyed by wildfire. These buildings were located at the Dorrance Ranch site and Marks Cabin site. The intent of this project is to cleanup and remove the unburned building components and contents. The sites are very remote with only motorized trail access to the Dorrance site, and non-motorized trail access to the Marks site. Thus, it is anticipated that the majority of the materials will have to be removed via helicopter sling loads.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | These remote buildings were used by trail maintenance crews in support of the Forest Recreation Program. There is no intent or desire to reconstruct these buildings. The sites of these buildings are close to the Hells Canyon Wilderness boundary. By cleaning up these sites and removing the debris, the potential for some of it (i.e. metal roofing panels) to migrate into the established wilderness area will be eliminated.
Design/construction specs: | Site cleanup with proper disposal and recycling of destroyed building materials and contents.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Dorrance Site Buildings | 15000 | 3 | 45000
Marks Site Building | 15000 | 1 | 15000
HABS survey for Sec 106 clearance | 15000 | 2 | 30000
0
0
0
Total funding requested: |  |  | 90000

## Burned Buildings Cleanup Low
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Rec Facilities
Activity Name: | Burned Recreation Buildings and Site Cleaup
Describe the fire damage and how the project is addressing that specific damage: | Within the Double Creek Fire area, the Forest had four recreation program support buildings destroyed by wildfire. These buildings were located at the Schaefer site and Granny View site. The intent of this project is to cleanup and remove the unburned building components and contents. The sites are very remote with only motorized trail access to the Dorrance site, and non-motorized trail access to the Marks site. Thus, it is anticipated that the majority of the materials will have to be removed via helicopter sling loads.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | These remote buildings have not been occupied or used for several years. There is no intent or desire to reconstruct these buildings. The sites of these buildings are close to the Hells Canyon Wilderness boundary. By cleaning up these sites and removing the debris, the potential for some of it (i.e. metal roofing panels) to migrate into the established wilderness area will be eliminated.
Design/construction specs: | Site cleanup with proper disposal and recycling of destroyed building materials and contents.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Schaeffer Site Building | 15000 | 1 | 15000
Granny View Site Building | 5000 | 1 | 5000
HABS survey for Sec 106 clearance | 15000 | 1 | 15000
0
0
0
Total funding requested: |  |  | 35000
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: how is this different than the high priority sites? is Granny View site near a road (lower cost)? The decsription is the same as for the high priority sites Reply: The difference is - high priority were buildings being USED. Low priority buildings were being unused at the time of the fires. which is part of the BAR guidance - we didn't want to exclude them though because I personally feel (Mary) like they should qualify. Reply: granny view is much more accessible and cost is lower

## Double Creek Rec Site Repairs
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Rec Facilities
Activity Name: | Double Creek Rec Site Repairs
Describe the fire damage and how the project is addressing that specific damage: | The fire burned recreation site infrastructure at 5 sites including Granny View Overlook, Horse Creek Overlook, Five Mile Viewpoint, Freezeout Trailhead & the Pittsburg rec site. Damage includes 6 interpretive panels and sign bases, 8 benches, 2 water systems (springs boxes & distribution lines) and 2 toilet vent pipes. This project will repair and replace damaged and destroyed items using sustainable recreation site design principles and fire-wise materials where appropriate.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | All five sites and damaged/destroyed intrastructure were in place and operational pre-fire. Horse Creek Viewpoint & Five Mile Overlook are Class 2 on the development scale. Granny View, Freezeout and Pittsburg are Class 3 with treatments restricted to minor features.
Design/construction specs: | Design/specs will utilize best practices from the Sustainable Recreation Site Design Guide, as well as engineered specifications from the Forest Facilities Engineer for water system repair. Fire-wise materials incorporated into the infrastructure replacements will be specified for all new materials incorporated into the repairs and replacements.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Interpretive Panels & kiosks | 5000 | 6 | 30000
Benches | 1000 | 8 | 8000
Toilet vent Pipe | 900 | 2 | 1800
2" Water Pipe | 4.4 | 3600 | 15840
Spring Box | 3000 | 2 | 6000
Water Pipe Couplers | 27 | 16 | 432
Water Pipe Clamps | 3 | 32 | 96
Water System Installation | 20000 | 2 | 40000
Section 106 consultation effort for bridge construction, recreation site reconstruction, water systems, range water developments etc. | 5000 | 3 | 15000
0
Total funding requested: |  |  | 117168
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: fire resilient material? e.g. concrete benches, metal spring box and distribution lines? Reply: Yes. Updated to include that in the design/construction specs 2/27/23

## Double Creek Signs
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Signs
Activity Name: | Double Creek Signs
Describe the fire damage and how the project is addressing that specific damage: | The fire burned over 149 trail signs and 2 Developed Recreation site entrance signs, resulting in a significant loss of signs. Large entrance signs and bases at both rec sites were confirmed as destroyed. 117 routed oak trail signs have been identified as fire-damaged based on an analysis of the number of signs located in fire areas with 50% basal area timber stand mortality, moderate to high burn severity & initial observations/reports. This project will replace all damaged signs to standard.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | Signs/markers were in place, operational and met sign/marker standards prefire.
Design/construction specs: | Replacement signs will meet current sign standards and use fire-wise materials for bases where appropriate. Signs installation is anticipated using contracted services.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Developed Rec Site Signs & Bases | 4000 | 2 | 8000
Trail sign | 150 | 117 | 17550
Trail sign post | 16 | 94 | 1504
Trail sign hardware | 1 | 250 | 250
Trail sign installation | 164 | 117 | 19188
0
Total funding requested: |  |  | 46492

## Nebo Signs
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Signs
Activity Name: | Nebo Trail Signs
Describe the fire damage and how the project is addressing that specific damage: | The fire perimeter included 6 trail signs. All 6 routed oak trail signs have been identified as fire-damaged based on an analysis of the number of signs located in fire areas with 50% basal area timber stand mortality, moderate to high burn severity & initial observations/reports. This project will replace all damaged signs to standard.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | Signs/markers were in place, operational and met sign/marker standards prefire.
Design/construction specs: | Replacement signs will meet current sign standards and use fire-wise materials for bases where appropriate. Signs installation is anticipated using contracted services.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Trail sign | 150 | 6 | 900
Trail sign post | 16 | 5 | 80
Trail sign hardware | 1 | 12 | 12
Trail sign installation | 164 | 6 | 984
0
0
Total funding requested: |  |  | 1976

## Sturgill Signs
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Signs
Activity Name: | Sturgill Trail Signs
Describe the fire damage and how the project is addressing that specific damage: | The fire perimeter included 8 trail signs. All 8 routed oak trail signs have been identified as fire-damaged based on an analysis of the number of signs located in fire areas with 50% basal area timber stand mortality, moderate to high burn severity & initial observations/reports. This project will replace all damaged signs to standard.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | Signs/markers were in place, operational and met sign/marker standards prefire.
Design/construction specs: | Replacement signs will meet current sign standards and use fire-wise materials for bases where appropriate. Signs installation is anticipated using contracted services.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Trail sign | 150 | 8 | 1200
Trail sign post | 16 | 6 | 96
Trail sign hardware | 1 | 16 | 16
Trail sign installation | 164 | 8 | 1312
0
0
Total funding requested: |  |  | 2624
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: should this be 8? previous tabs had one unit of installation per sign Reply: Changed trail sign installation from 16 to 8 per discussion with John Hollenbeak 2/27/23

## Double Creek Trail Repair
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Trails
Activity Name: | Double Creek Trail Repair
Describe the fire damage and how the project is addressing that specific damage: | The fire perimeter includes over 278 miles of system trail. 108 miles of trail have been identified as fire-damaged based on an analysis of the number miles located in fire areas with >75% basal area timber stand mortality, moderate to high burn severity & initial observations/reports. Fire-damaged trail tread from burned stumps/tree roots have created very hazardous footing for hikers and stock. Fire damage also includes significant additional logout in some portions of fire area due to fire-weakened trees. Additionally, minor trail features such as drainage structures have been compromised by fire. This project will repair tread where burned out, remove burned brush and debris from trail tread, repair/clean fire-damaged features, and remove fire damaged trees from trail.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | All trail features were in place and operational pre-fire. Replacement/repair of features are limited to Class 2-3 trails and work would be consistent with Standard Trail Plans and Specification. Replacement/repair would be limited to infrastructure defined as Minor Trail Bridge, or Trail Structure.
Design/construction specs: | Restore trails to pre-fire Class 2-3 maintenance specs. Includes tread, drainage structure, & logout specifications
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Trail repair | 2500 | 108 | 270000
0
0
0
0
0
Total funding requested: |  |  | 270000

## Double Creek Trail Boardwalks
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Trails
Activity Name: | Double Creek Trail Boardwalk Reconstruction
Describe the fire damage and how the project is addressing that specific damage: | The fire entirely burned two elevated boardwalks on the trail loop at Granny View Overlook. The West structure had a full-length railing and was 85' long and 5' wide, with a 14'x10' viewing platform in the middle. The North structure was 40' long and 5' wide with a single railing. This project will replace these structures using fire-wise materials and remove the debris from the burned structures.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | These structures were in place and operational pre-fire (see photos). They're located along a Class 4 trail and management has occurred at designated frequencies. Replacement would be consistent with Standard Trail Plans and Specifications and replacement would be restricted to Other Engineered Trail Structure.
Design/construction specs: | Reconstruct to same size & location per engineered design using fire-wise materials for sub-structures to minimize effects from future fire and reduce long-term maintenance. Retain existing asphalt trail surface.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | N/A
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
North Boardwalk | 425 | 210 | 89250
West Boardwalk | 425 | 495 | 210375
Debris Removal | 3000 | 2 | 6000
0
0
0
Total funding requested: |  |  | 305625

## Nebo Trail Repair
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Trails
Activity Name: | Nebo Trail Repair
Describe the fire damage and how the project is addressing that specific damage: | The fire perimeter includes over 18 miles of system trail. 4 miles of trail have been identified as fire-damaged based on an analysis of the number miles located in fire areas with >75% basal area timber stand mortality, moderate to high burn severity & initial observations/reports. Fire-damaged trail tread from burned stumps/tree roots have created very hazardous footing for hikers and stock. Fire damage also includes significant additional logout in some portions of fire area due to fire-weakened trees. Additionally, minor trail features such as drainage structures have been compromised by fire. This project will repair tread where burned out, remove burned brush and debris from trail tread, repair/clean fire-damaged features, and remove fire damaged trees from trail. Trail repair in Nebo is higher than Double Creek because of distance to sites in the wilderness. Trails that are opened already may still take take a full day to get to each individual site. Likely some trail work would have to be performed to establish access, though its likely less than Sturgil and more than Double Creek.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | All trail features were in place and operational pre-fire. Replacement/repair of features are limited to Class 2-3 trails and work would be consistent with Standard Trail Plans and Specification. Replacement/repair would be limited to infrastructure defined as Minor Trail Bridge, or Trail Structure.
Design/construction specs: | Restore trails to pre-fire Class 2-3 maintenance specs. Includes tread, drainage structure, & logout specifications
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Trail repair | 4063 | 4 | 16252
0
0
0
0
0
Total funding requested: |  |  | 16252

## Nebo Trail Bridges
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Trails
Activity Name: | Nebo Trail Bridges Reconstruction
Describe the fire damage and how the project is addressing that specific damage: | The Fire severely burned timbered basins upslope of two trail bridges along the Tenderfoot Wagon Road Trail #1819. A significant rain event during the fire caused debris flows that washed out the bridges. Both trail bridges were wood structures designed for pack & saddle use and were 7' wide. One bridge was 24' long and the other 18' long.This project will replace both bridges using fire-wise materials and remove debris from demolished bridges.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | These structures were in place and operational pre-fire (see photos). They're located along a Class 3 trail and maintenance has exceeded designated frequencies (performed annually by the Wallowa Mountains Ski Club). Replacement would be consistent with Standard Trail Plans and Specifications and replacement would be restricted to Other Engineered Trail Structures.
Design/construction specs: | Per engineered design: steel girder sub-structure (12X19 WF) and sills; curbs w/no railings; snowload: 181 psf; 1.75 X 181 = 317 psf; material transport by ATV; unit cost based on recent TB construction.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Trail Bridge #3 | 400 | 168 | 67200
Trail Bridge #2 | 400 | 126 | 50400
Removal of damaged structure | 5000 | 2 | 10000
Section 106 consultation effort for bridge construction, recreation site reconstruction, water systems, range water developments etc. | 5000 | 3 | 15000
0
0
Total funding requested: |  |  | 142600
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: if fire did not damage the bridge directly it likely is not eligible for BAR Reply: One bridge DID burn the other likely burned (was located in mod/high SBS mosaic burn) however it was washed away during a rain event before the BAER team assembled. It was not able to be located because of safety. I'm checking with recreation shop to see if someone did see the bridge before it was washed out.

## Sturgill Trail Repair
Activity Information Template
Category: | Category 1 - Minor Facilities and Infrastructure
Project Type: | Trails
Activity Name: | Sturgill Trail Repair
Describe the fire damage and how the project is addressing that specific damage: | The fire perimeter includes over 36 miles of system trail. 3 miles of trail have been identified as fire-damaged based on an analysis of the number miles located in fire areas with >75% basal area timber stand mortality, moderate to high burn severity & initial observations/reports. Fire-damaged trail tread from burned stumps/tree roots have created very hazardous footing for hikers and stock. Fire damage also includes significant additional logout in some portions of fire area due to fire-weakened trees. Additionally, minor trail features such as drainage structures have been compromised by fire. This project will repair tread where burned out, remove burned brush and debris from trail tread, repair/clean fire-damaged features, and remove fire damaged trees from trail. Cost for Sturgil trail repair is different for the other fires because the work is more spread out and takes much longer to get out there. For instance if the trails are opened already it would still take a full day to get to each individual site. likely some trail work would have to be performed to establish access.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | All trail features were in place and operational pre-fire. Replacement/repair of features are limited to Class 2-3 trails and work would be consistent with Standard Trail Plans and Specification. Replacement/repair would be limited to infrastructure defined as Minor Trail Bridge, or Trail Structure.
Design/construction specs: | Restore trails to pre-fire Class 2-3 maintenance specs. Includes tread, drainage structure, & logout specifications
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Trail repair | 6300 | 3 | 18900
0
0
0
0
0
Total funding requested: |  |  | 18900
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: unit cost difference between the fires? economy of scale, access, pack stock needs partners, amount of logout? some reasoning would be beneficial Reply: I asked Recreation just now. Sturgill is in the wilderness so any trail repair will likely require pack stock needs and having help from partners. It likely is just more costly because of access but I did ask Recreation folks to provide more detail on cost/unit difference for sturgill. Reply: Sturgill trail cost is due to the work being more spread out and takes alot more work just to get there. for instance if the trails are opened already it would still take a full day to get to each individual site. likely some trail work would have to be performed to establish access. Reply: I did add some description of the additional work that is associated with Nebo and Sturgil. They are higher and it all has to do with access.

## InvPlant_Protect_Double
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Invasive Plant Treatments
Activity Name: | Protection Area Invasive Plant Treatments
Describe the fire damage and how the project is addressing that specific damage: | Fire creates conditions favorable for the invasion of invasive plants. In areas where vegetation mortality is greater than 50%, it is unlikely the native vegetation will re-establish and outcompete invasive plants. Outyear invasive plant monitoring and treatments will foster the recovery of these native plant communities while minimizing the invasion potential into their habitat.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Wallowa Whitman National Forest will be following the WAW Invasive Plant Treatment Project that tiers to the R6 FEIS and R6 ROD that tiers to FSM 2900. Project Design Features are in place to eliminate or minimize the effects of invasive plant treatments on human health and natural resources. The PDFs allow the treatment of existing and new (EDRR) sites and species in accordance with R6 ROD Standards 19 and 20.
Design/construction specs: | Utilize current IDIQ contract and partnership agreements to treat invasive plants
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Invasive Plant treatments in Protection areas (Bunchgrass/TESP) YEAR 2 | 400 | 31 | 12400
Invasive Plant treatments in Protection areas (Bunchgrass/TESP) YEAR 3 | 400 | 31 | 12400
0
0
0
0
Total funding requested: |  |  | 24800

## InvPlant_Suppression_Double
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Invasive Plant Treatments
Activity Name: | Suppression and Disturbance Invasive Plant Treatments Double Creek
Describe the fire damage and how the project is addressing that specific damage: | The spread of invasive plants is a significant issue in projects that involve ground disturbance. Earth moving activities, in this case, dozer lines and hand lines can contribute to the spread of weeds. Material has the potential to move off site on equipment, disrupt the weed seed bed that was once covered by soil, and expose the ground for the invasion of weeds. The proximity and existence of already identified noxious weed species sites will increase the risk of further establishment. Due to rapid growth rates, high seed production, and extended growing periods of noxious weeds, ground disturbances created can easily be colonized by invasive plants.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Wallowa Whitman National Forest will be following the WAW Invasive Plant Treatment Project that tiers to the R6 FEIS and R6 ROD that tiers to FSM 2900. Project Design Features are in place to eliminate or minimize the effects of invasive plant treatments on human health and natural resources. The PDFs allow the treatment of existing and new (EDRR) sites and species in accordance with R6 ROD Standards 19 and 20.
Design/construction specs: | Utilize current IDIQ contract and partnership agreements to treat invasive plants
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 1) | 300 | 55 | 16500
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 2) | 300 | 55 | 16500
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 2) | 300 | 55 | 16500
0
0
0
Total funding requested: |  |  | 49500
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: suppression repair EDRR is covered in 2500-8. How is this different? as written and expressed it seems to be continuation of approved BAER activities and would be appropriate for years 2 and 3.
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same number of acres and unit cost per acre as the 2500-8 BAER report

## InvPlant_Suppression_Nebo
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Invasive Plant Treatments
Activity Name: | Suppression and Disturbance Invasive Plant Treatments Nebo
Describe the fire damage and how the project is addressing that specific damage: | The spread of invasive plants is a significant issue in projects that involve ground disturbance. Earth moving activities, in this case, Dozer lines and hand lines can contribute to the spread of weeds. Material has the potential to move off site on equipment, disrupt the weed seed bed that was once covered by soil, and expose the ground for the invasion of weeds. The proximity and existence of already identified noxious weed species sites will increase the risk of further establishment. Due to rapid growth rates, high seed production, and extended growing periods of noxious weeds, ground disturbances created can easily be colonized by invasive plants.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Wallowa Whitman National Forest will be following the WAW Invasive Plant Treatment Project that tiers to the R6 FEIS and R6 ROD that tiers to FSM 2900. Project Design Features are in place to eliminate or minimize the effects of invasive plant treatments on human health and natural resources. The PDFs allow the treatment of existing and new (EDRR) sites and species in accordance with R6 ROD Standards 19 and 20.
Design/construction specs: | Utilize current IDIQ contract and partnership agreements to treat invasive plants
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 1) | 300 | 17 | 5100
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 2) | 300 | 17 | 5100
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 3) | 300 | 17 | 5100
0
0
0
Total funding requested: |  |  | 15300
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: since there was no suppression EDRR requested/approved for Sturgill and Nebo include what this covers that would not have been covered in BAER

## InvPlant_Suppression_Sturgil
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Invasive Plant Treatments
Activity Name: | Suppression and Disturbance Invasive Plant Treatments Sturgil
Describe the fire damage and how the project is addressing that specific damage: | The spread of invasive plants is a significant issue in projects that involve ground disturbance. Earth moving activities, in this case, Dozer lines and hand lines can contribute to the spread of weeds. Material has the potential to move off site on equipment, disrupt the weed seed bed that was once covered by soil, and expose the ground for the invasion of weeds. The proximity and existence of already identified noxious weed species sites will increase the risk of further establishment. Due to rapid growth rates, high seed production, and extended growing periods of noxious weeds, ground disturbances created can easily be colonized by invasive plants.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Wallowa Whitman National Forest will be following the WAW Invasive Plant Treatment Project that tiers to the R6 FEIS and R6 ROD that tiers to FSM 2900. Project Design Features are in place to eliminate or minimize the effects of invasive plant treatments on human health and natural resources. The PDFs allow the treatment of existing and new (EDRR) sites and species in accordance with R6 ROD Standards 19 and 20.
Design/construction specs: | Utilize current IDIQ contract and partnership agreements to treat invasive plants
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 1) | 300 | 57 | 17110
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 2) | 300 | 57 | 17110
Invasive Plant EDRR treatment of all ground disturbing points and lines (YEAR 3) | 300 | 57 | 17100
0
0
0
Total funding requested: |  |  | 51320

## DoubleCreek_Seeding
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Revegetation
Activity Name: | Double Creek Preventative Native Seeding
Describe the fire damage and how the project is addressing that specific damage: | Fire creates conditions favorable for the invasion of invasive plants. In sensitive plant areas where vegetation mortality is greater than 75%, it is unlikely the native vegetation will re-establish and outcompete invasive plants. Native seeding will increase the density of native bunchgrass and help foster the recovery of these native plant communities while minimizing the invasion potential into their habitat. Suppression activities have created conditions favorable to invasive plant invasion. Vegetation will be re-established on all bare ground and treated acres in sensitive plant areas to minimize weed spread and establishment.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Pacific NW R6 ROD decision adds invasive plant management direction to all National Forest Land and Resource Management Plans in the Pacific Northwest Region (Region Six). The management direction includes invasive plant prevention and treatment/restoration standards intended to help achieve stated desired future conditions, goals and objectives. Treatment Restoration standards are in place for this proposed activity, specifically Standard 13, where native plant materials will be used for seeding.
Design/construction specs: | Recommended seeding rates at 20lbs per acre. Native seed is available from BFI. Species used will be bluebunch wheatgrass, Idaho fescue, prairie junegrass, and sandberg's bluegrass. Work will be contracted out, utilizing current IDIQ contract and partnership agreements.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance • Area of past restoration investment (i.e. floodplain restoration or habitat restoration efforts) • Provides value to multiple partners and stakeholder interest groups, especially tribes, minority, low income
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Double Creek Protection Areas Native Seeding | 400 | 31 | 12400
Double Creek Suppression Disturbance Native Seeding | 400 | 55 | 22000
0
0
0
0
Total funding requested: |  |  | 34400

## Nebo_Seeding
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Revegetation
Activity Name: | Nebo Fire Preventative Native Seeding
Describe the fire damage and how the project is addressing that specific damage: | Fire creates conditions favorable for the invasion of invasive plants. Native seeding will increase ground cover and help foster the recovery of native plant species while minimizing the invasion potential into their habitat. Suppression activities have created conditions favorable to invasive plant invasion. Vegetation will be re-established on all bare ground and disturbances resulting from suppression activities.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Pacific NW R6 ROD decision adds invasive plant management direction to all National Forest Land and Resource Management Plans in the Pacific Northwest Region (Region Six). The management direction includes invasive plant prevention and treatment/restoration standards intended to help achieve stated desired future conditions, goals and objectives. Treatment Restoration standards are in place for this proposed activity, specifically Standard 13, where native plant materials will be used for seeding.
Design/construction specs: | Recommended seeding rates at 20lbs per acre. Native seed is available from BFI. Species used will be bluebunch wheatgrass, Idaho fescue, prairie junegrass, and sandberg's bluegrass. Work will be contracted out, utilizing current IDIQ contract and partnership agreements.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance • Area of past restoration investment (i.e. floodplain restoration or habitat restoration efforts) • Provides value to multiple partners and stakeholder interest groups, especially tribes, minority, low income
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Nebo Suppression Disturbance Native Seeding | 400 | 17 | 6800
0
0
0
0
0
Total funding requested: |  |  | 6800

## Sturgil_Seeding
Activity Information Template
Category: | Category 2 - Lands Unlikely to Recover Naturally
Project Type: | Revegetation
Activity Name: | Sturgil Fire Preventative Native Seeding
Describe the fire damage and how the project is addressing that specific damage: | Fire creates conditions favorable for the invasion of invasive plants. Native seeding will increase ground cover and help foster the recovery of native plant species while minimizing the invasion potential into their habitat. Suppression activities have created conditions favorable to invasive plant invasion. Vegetation will be re-established on all bare ground and disturbances resulting from suppression activities.
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document. | The Pacific NW R6 ROD decision adds invasive plant management direction to all National Forest Land and Resource Management Plans in the Pacific Northwest Region (Region Six). The management direction includes invasive plant prevention and treatment/restoration standards intended to help achieve stated desired future conditions, goals and objectives. Treatment Restoration standards are in place for this proposed activity, specifically Standard 13, where native plant materials will be used for seeding.
Design/construction specs: | Recommended seeding rates at 20lbs per acre. Native seed is available from BFI. Species used will be bluebunch wheatgrass, Idaho fescue, prairie junegrass, and sandberg's bluegrass. Work will be contracted out, utilizing current IDIQ contract and partnership agreements.
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document. | • Continuation of post-fire investments made through BAER • Designated T&E critical habitat or occupied habitat for T&E, Proposed, or Candidate species • Small-scale ecosystems or rare plant communities • Benefits pollinators and pollinator habitat • Regional Forester sensitive species, species of conservation concern, or other habitat of importance • Area of past restoration investment (i.e. floodplain restoration or habitat restoration efforts) • Provides value to multiple partners and stakeholder interest groups, especially tribes, minority, low income
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
Sturgil Suppression Disturbance Native Seeding | 400 | 57 | 22800
0
0
0
0
0
Total funding requested: |  |  | 22800

## Lists (hidden)
Category 1 - Minor Facilities and Infrastructure | Signs | Repair | High
Category 2 - Lands Unlikely to Recover Naturally | Landline Boundary | Replace | Moderate
| Gates | New | Low
Roads
Trails
Rec Facilities
Range
Non-Range Fences
Wildlife/Fisheries
Other Minor Facilities
Revegetation
Reforestation
Invasive Plant Treatments

## ProjectActivityInformation
Activity Information Template
Category:
Project Type:
Activity Name:
Describe the fire damage and how the project is addressing that specific damage:
How does the project meet the category specific requirements for funding? Activity type requirements are found in the guidance document.
Design/construction specs:
For Category 2 projects, please list the priority concerns the project is able to address. The list of priority concerns is found in the guidance document.
Project Estimates (add lines if needed):
Item | Cost/unit | Units needed | Cost
0
0
0
0
0
0
Total funding requested: |  |  | 0

## Sheet2
Fire Name | Sum of Funds Requested
Double Creek | 1544731.46
Nebo | 182928
Sturgil | 74100
Sturgill | 21524
Grand Total | 1823283.46